## Sheet1
SP 2021 Bachelor Project		Name: Claudio Maggioni Advisor: Prof. Walter Binder Co-advisor: Dr. Andrea Rosa’

Below the status report table can be found. In order to understand the table better, I will give some details regarding my thesis. My thesis is essentially divided in two parts. The first part is essentially a Data Engineering-like project where I need to design, code, and run several queries (i.e. one query per activity) on a data set roughly sized at 8 TiB and divided in 8 “clusters” (below identified by letters A-H). The same query will be executed on the 8 different clusters independently, so that’s why the table below shows a “status” for each cluster. Please consult the legend at the bottom of the document in order to understand the exact state of execution of any specific query (i.e. activity). Activities that do not have query and cluster status are related to the analysis and creation of the thesis report, which is the second part of my bachelor project.

Activity name	Status	Total est. effort (hours)	Estimated remaining effort		Status per cluster					Results’ folder name (for Dr. Rosa’)
			work ETA (hours)	computation ETA (on a single machine)	A	B	C	D	E	F	G	H
Table I: Table of distinct CPU/Memory configurations of machines and theirdistribution	DONE	12	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	machine_configs
III-A Figure 3: Temporal impact: machine time waste:	DONE	12	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	machine_time_waste
III-A-I Table II: Average slowdown per task	DONE	12	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	task_slowdown
III-B: Spatial impact: resource waste (requested usage)	DONE	0	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	spatial_resource_waste
III-B: Spatial impact: resource waste (actual usage)	DOING	6	3	24 hours * 4	D	D	D	D	B	B	B	B	spatial_resource_waste
V-A Figure 7: Event rates vs. task priority	DONE	12	1	6 hours * 7	D	D	D	D	D	D	D	D	figure_7
V-A Figure 7: Event rates vs. task priority, event execution time	DONE	12	1	Took ~24 hours * 8	D	D	D	D	D	D	D	D	figure_7
V-A Figure 7: Event rates vs. machine concurrency	TODO	12	8	4 hours * 1	R	S	S	S	S	S	S	S	figure_7
V-B Figure 8: Event rates vs. requested resources	DOING	8	2		N	N	N	N	N	N	N	N	figure_8
V-B Figure 8: Event rates vs. resource reservation	DOING	8	1		N	S	S	S	B	B	B	B	figure_8
V-B Figure 8: Event rates vs resource utilization	DOING	8	1		N	N	N	N	B	B	B	B	figure_8
V-C Figure 9: Job rates vs job size, job execution time and machine locality	TODO	4	4	8 hours * 8	--	--	--	--	--	--	--	--	figure_9
V-C Figure 9: Job rates vs job size, job execution time and machine locality	TODO	4	4	8 hours * 8	--	--	--	--	--	--	--	--	figure_9
V-C Figure 9: Job rates vs job size, job execution time and machine locality	TODO	4	4	24 hours * 8	--	--	--	--	--	--	--	--	figure_9
Analysis of obtained results (with Dr. Rosa’)	TODO	6	12	No computation needed
Report writing (introduction and motivation for analysis)	TODO	12	6	No computation needed
Report writing (introduction of domain specific knowledge, e.g. source and meaning of data)	TODO	12	12	No computation needed
Report writing (analysis description session for machine_configs, machine_time_waste, spatial_resource_waste, task_slowdown)	TODO	12	12	No computation needed
Report writing (analysis description session, potential causes of unsuccesful executions – i.e. figures 7,8,9)	TODO	12	12	No computation needed
Report writing (Conclusion and comparison with 2011 data)	TODO	6	6	No computation needed
TOTAL:		174	89

Note: data for clusters E-H is stored on a machine which I will be able to access this Tuesday (tomorrow). I will then copy the data and complete the unfinished analysis

Legend of states for each cluster:
D	The Analysis is done;
N	The CPU expensive part of the computation is done, but graphs, figures, and summary tables must still be generated to present the data nicely;
R	The CPU intensive analysis script is execution in this moment;
B	Blocked by the the instance_usage traces stored on w
S	The CPU intensive script is ready to be executed and awaits a free machine from DAG’s server pool to execute;
C	The CPU intensive script has been scheduled but is not yet in execution
--	The analysis script’s code has not been written/completed yet.