## Sheet1
SP 2021 Bachelor Project	Status Report		Name: Claudio Maggioni Advisor: Prof. Walter Binder Co-advisor: Dr. Andrea Rosa’

Below the status report table can be found. In order to understand the table better, I will give some details regarding my thesis. My thesis is essentially divided in two parts. The first part is essentially a Data Engineering-like project where I need to design, code, and run several queries (i.e. one query per activity) on a data set roughly sized at 8 TiB and divided in 8 “clusters” (below identified by letters A-H). The same query will be executed on the 8 different clusters independently, so that’s why the table below shows a “status” for each cluster. Please consult the legend at the bottom of the document in order to understand the exact state of execution of any specific query (i.e. activity). Activities that do not have query and cluster status are related to the analysis and creation of the thesis report, which is the second part of my bachelor project.

Activity name	Importance	Status	Total est. effort (hours)	Estimated remaining effort		Status per cluster					Results’ folder name (for Dr. Rosa’)
				work ETA (hours)	computation ETA (on a single machine)	A	B	C	D	E	F	G	H
Table I: Table of distinct CPU/Memory configurations of machines and theirdistribution	NEEDED	DONE on time	12	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	machine_configs
III-A Figure 3: Temporal impact: machine time waste:	NEEDED	DONE on time	12	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	machine_time_waste
III-A-I Table II: Average slowdown per task	NEEDED	DONE on time	12	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	task_slowdown
III-B: Spatial impact: resource waste (requested usage)	NEEDED	DONE on time	0	0	Took ~12 hours * 8	D	D	D	D	D	D	D	D	spatial_resource_waste
III-B: Spatial impact: resource waste (actual usage)	NEEDED	DOING	6	3	24 hours * 4	D	D	D	D	S	S	S	S	spatial_resource_waste
V-A Figure 7: Event rates vs. task priority, event execution time	NEEDED	DOING	12	1	Took ~24 hours * 8	N	N	N	N	N	N	N	N	figure_7
V-A Figure 7: Event rates vs. machine concurrency	OPTIONAL	TODO	12	12	24 hours * 8	--	--	--	--	--	--	--	--	figure_7
V-B Figure 8: Event rates vs. requested resources	NEEDED	DOING (delayed)	8	2	12 hours (for A) + 24 hours * 7	R	S	S	S	S	S	S	S	figure_8
V-B Figure 8: Event rates vs. resource reservation	NEEDED	DOING (delayed)	8	2	12 hours (for A) + 24 hours * 7	R	S	S	S	S	S	S	S	figure_8
V-B Figure 8: Event rates vs resource utilization	NEEDED	DOING (delayed)	8	2	12 hours (for A) + 24 hours * 7	R	S	S	S	S	S	S	S	figure_8
V-C Figure 9: Job rates vs job size, job execution time and machine locality	OPTIONAL	TODO	4	4	8 hours * 8	--	--	--	--	--	--	--	--	figure_9
V-C Figure 9: Job rates vs job size, job execution time and machine locality	OPTIONAL	TODO	4	4	8 hours * 8	--	--	--	--	--	--	--	--	figure_9
V-C Figure 9: Job rates vs job size, job execution time and machine locality	OPTIONAL	TODO	4	4	24 hours * 8	--	--	--	--	--	--	--	--	figure_9
Analysis of obtained results (with Dr. Rosa’)	NEEDED	TODO	6	12	No computation needed
Report writing (introduction and motivation for analysis)	NEEDED	TODO	12	6	No computation needed
Report writing (introduction of domain specific knowledge, e.g. source and meaning of data)	NEEDED	TODO	12	12	No computation needed
Report writing (analysis description session for machine_configs, machine_time_waste, spatial_resource_waste, task_slowdown)	NEEDED	TODO	12	12	No computation needed
Report writing (analysis description session, potential causes of unsuccesful executions – i.e. figures 7,8,9)	NEEDED	TODO	12	12	No computation needed
Report writing (Conclusion and comparison with 2011 data)	NEEDED	TODO	6	6	No computation needed
TOTAL:			162	94

Note: data for clusters E-H is stored on a machine which I will be able to access this Tuesday (tomorrow). I will then copy the data and complete the unfinished analysis

Legend of states for each cluster:
D	The Analysis is done;
N	The CPU expensive part of the computation is done, but graphs, figures, and summary tables must still be generated to present the data nicely;
R	The CPU intensive analysis script is execution in this moment;
S	The CPU intensive script is ready to be executed and awaits a free machine from DAG’s server pool to execute;
--	The analysis script’s code has not been written/completed yet.